## Backlog status
Backlog status - development done or not, story by story
Stories, epics, priority, phase and effort are copied from 'CDI-Adapter-Epic-Backlog-UploadScreen-v6-FINAL'. The status columns are from the tests and measured runs in the repository, as of 2026-10-10.
Legend - Yes: built, every acceptance criterion passes in tests. Yes - open items: built, but one or more criteria are partial or wait on something from outside (named in the last columns). Partly: some of it is built. No: not taken up yet.
Story ID | Epic | Title | Priority | Phase | Effort pd (ESTIMATE) | Story points | Repo status in the v6 workbook (2026-10-04) | Development done? | Acceptance criteria passing | What is still open | Proof (tests / documents)
UP-S1 | UP Scan & upload screen | Choose, scan or take a picture of the pages and send them | Must | 1 | 5 | 8 | Partial | Yes | 6 of 6 | Not tried on a real phone. | tests/test_up_s1_acceptance_unit.py (50 passed); docs/test-UP-S1.md
UP-S2 | UP Scan & upload screen | Tell the person at once if a picture is not good enough, and let them retake just that page | Must | 1 | 3 | 5 | Partial | Yes | 5 of 5 | Weekly retake report not yet run on a real database. | tests/test_up_s2_acceptance_unit.py (38 passed); docs/test-UP-S2.md
UP-S3 | UP Scan & upload screen | Show the result on the screen and let the person download the JSON | Should | 2 | 5 | 8 | Partial | Yes | 5 of 5 | Report-a-wrong-result not yet run on a real database. | tests/test_up_s3_acceptance_unit.py (67 passed); docs/test-UP-S3.md
LS-S1 | LS File listener (watched folder) | Watch a folder on OneDrive, SharePoint, Google Drive or this computer, chosen by settings only | Must | 1 | 2 | 3 | Built | Yes - open items | 3 of 4 | AC2: the retry-agent half was never re-checked. Cloud drives tested against stand-ins only. | tests/test_ls_s1_acceptance_unit.py; docs/test-LS-S1.md
LS-S2 | LS File listener (watched folder) | Sign in to the drive safely (no password handled by us) | Must | 1 | 3 | 5 | Partial | Yes - open items | 3 of 4 | AC2: an expired sign-in raises an alert but does not message a person. No real Microsoft account or Entra app yet. | tests/test_listener_auth_unit.py; docs/test-LS-S2.md
LS-S3 | LS File listener (watched folder) | Pick up only finished, new, allowed files | Must | 1 | 2 | 3 | Partial | Yes | 5 of 5 | The same-file rule in the database is covered by a test that is skipped on the dev PC. | tests/test_ls_s3_acceptance_unit.py (58 passed); docs/test-LS-S3.md
LS-S4 | LS File listener (watched folder) | Read each image or PDF with the same OCR steps as the upload screen | Must | 1 | 3 | 5 | Partial | Yes - open items | 3 of 5 | AC1 and AC4: the saved document, and screen-against-folder results, were never compared on a database. | tests/test_ls_s4_acceptance_unit.py; docs/test-LS-S4.md
LS-S5 | LS File listener (watched folder) | Run files in batches of three | Must | 1 | 1 | 2 | Built | Yes | 4 of 4 | None. | tests/test_ls_s5_acceptance_unit.py (29 passed); docs/test-LS-S5.md
LS-S6 | LS File listener (watched folder) | File each prescription by outcome and keep only the failure reasons in a log folder | Must | 1 | 2 | 3 | Built | Yes | 5 of 5 | AC3 shown with a stand-in for the database. | tests/test_ls_s6_acceptance_unit.py; docs/test-LS-S6.md
LS-S7 | LS File listener (watched folder) | Retry a failed file 3 times, then hand it to a person | Must | 1 | 2 | 3 | Partial | Yes - open items | 3 of 4 | AC4: a quarantined file shows in the website banner, but nobody away from a screen is told (needs ENT-S4). | tests/test_ls_s7_acceptance_unit.py; docs/test-LS-S7.md
LS-S8 | LS File listener (watched folder) | Give the same database rows and JSON as an upload, and say where each result came from | Must | 1 | 2 | 3 | Partial | Yes | 4 of 4 | None. | tests/test_ls_s8_acceptance_unit.py (34 passed); docs/test-LS-S8.md
LS-S9 | LS File listener (watched folder) | Keep the listener running, restart-safe and visible | Should | 1 | 3 | 5 | Partial | Yes | 4 of 4 | Alerts reach the website banner only; no email, chat or pager. | tests/test_ls_s9_acceptance_unit.py; docs/test-LS-S9.md
LS-S10 | LS File listener (watched folder) | Prove it on a real drive and under load | Must | 1 | 3 | 5 | Not built | Yes - open items | 2 of 4 | AC1 and AC2 not run: the real OneDrive (Microsoft API) and Google Drive need the owner's Entra client id, a sign-in and a Google service account. | tests/test_ls_s10_acceptance_unit.py; docs/evidence/LS-S10/
IM-S1 | IM Image preparation (OpenCV) | Check every picture first (blur, glare, dark, small, sideways) | Must | 1 | 3 | 5 | Built | Yes - open items | 3 of 4 | AC3: the false-reject rate needs an answer-key set of real photographs. | tests/test_im_s1_acceptance_unit.py; docs/test-IM-S1.md
IM-S2 | IM Image preparation (OpenCV) | Straighten and crop the page safely, keeping the original untouched | Should | 1 | 4 | 5 | Partial | Yes - open items | 5 of 5 with the switch on | Off by default (CDI_STRAIGHTEN). On 21 real photos it turned an upright page upside down and missed sideways ones: needs rework before it is switched on. | tests/test_im_s2_acceptance_unit.py (44 passed); docs/test-IM-S2.md
IM-S3 | IM Image preparation (OpenCV) | Find the text lines and say which are printed and which are handwritten | Must | 1 | 3 | 5 | Built | Yes - open items | 3 of 4 | AC3: line recall and label accuracy need real pages with hand-drawn lines. Line-by-line reading is off by default. | tests/test_im_s3_acceptance_unit.py; docs/test-IM-S3.md
RD-S1 | RD Reading engines working together | Read printed text with RapidOCR | Must | 1 | 1 | 2 | Built | Yes | 2 of 2 | Printed lines are kept from the handwriting reader only with line-by-line reading on (off by default). | tests/test_rd_s1_acceptance_unit.py (21 passed); docs/test-RD-S1.md
RD-S2 | RD Reading engines working together | Handwriting: TrOCR and Qwen each read every line on their own | Must | 1 | 4 | 5 | Built | Yes - open items | 3 of 4 | AC4: the benchmark has run on synthetic lines only; 500-1,000 real handwritten lines must be typed first (kit built). TrOCR licence is a review item. | tests/test_rd_s2_acceptance_unit.py; docs/test-RD-S2.md
RD-S3 | RD Reading engines working together | If the readers disagree, or the picture does not support the answer, send it to a person | Must | 1 | 3 | 5 | Built | Yes | 5 of 5 | Unit level only: not run end to end with the real models. Thresholds are assumptions, not measured. | tests/test_rd_s3_acceptance_unit.py (37 passed)
RD-S4 | RD Reading engines working together | Qwen fills the structured form from the page, in valid JSON | Must | 1 | 4 | 5 | Built | Yes | 7 of 7 | Unit level only (stub model). Not built: pictures of pages 2+, automatic re-queue of an upload after out-of-memory, picture-size sweep, adversarial pictures. | tests/test_rd_s4_acceptance_unit.py (41 passed)
RD-S5 | RD Reading engines working together | Ten prescriptions at once, each finished within 1 minute, on one GPU | Must | 1 | 6 | 8 | Not built | Yes | 5 of 5 | Measured on fake printed prescriptions on one 32 GB GPU. The batching server's install needed a manual step on that host. | tests/test_rd_s5_acceptance_unit.py (16 passed); docs/evidence/RD-S5/
SW-S1 | SW Change any model or component | Put every engine and component behind a small written interface | Must | 1 | 5 | 8 | Partial | No | - | Not taken up yet. | -
SW-S2 | SW Change any model or component | Model registry: every model recorded, pinned and chosen by settings | Must | 1 | 3 | 5 | Not built | No | - | Not taken up yet. | -
SW-S3 | SW Change any model or component | Fine-tune any replacement model with the same data and one command | Must | 1 | 5 | 8 | Not built | No | - | Not taken up yet. | -
SW-S4 | SW Change any model or component | A fair contest: a new model against the current champion | Must | 1 | 5 | 8 | Not built | No | - | Not taken up yet. | -
SW-S5 | SW Change any model or component | Deploy the winner safely: shadow run, one-setting switch, one-step rollback | Must | 1 | 5 | 8 | Partial | No | - | Not taken up yet. | -
SW-S6 | SW Change any model or component | Replace any non-model component: PDF renderer, object store, queue, terminology, drive, sign-in | Should | 1 | 5 | 8 | Not built | No | - | Not taken up yet. | -
SW-S7 | SW Change any model or component | A licence and safety gate in front of every swap | Must | 1 | 3 | 5 | Not built | No | - | Not taken up yet. | -
EX-S1 | EX The four things we extract | Read the patient details | Must | 1 | 3 | 5 | Partial | No | - | Not taken up yet. | -
EX-S2 | EX The four things we extract | Read the doctor details | Must | 1 | 3 | 5 | Partial | No | - | Not taken up yet. | -
EX-S3 | EX The four things we extract | Read the lab tests that were ordered and give each a standard name | Must | 1 | 4 | 5 | Partial | No | - | Not taken up yet. | -
EX-S4 | EX The four things we extract | Read the lab preparation instructions | Must | 1 | 6 | 8 | Not built | No | - | Not taken up yet. | -
EX-S5 | EX The four things we extract | Say why each test was ordered (context) | Should | 2 | 4 | 5 | Not built | No | - | Not taken up yet. | -
EX-S6 | EX The four things we extract | Every value carries its proof and a status | Must | 1 | 2 | 3 | Built | No | - | Not taken up yet. | -
OUT-S1 | OUT Save & deliver (database + JSON) | Save everything to the database | Must | 1 | 3 | 5 | Partial | No | - | Not taken up yet. | -
OUT-S2 | OUT Save & deliver (database + JSON) | Also give every result as a JSON file with a fixed format | Must | 1 | 3 | 5 | Not built | Partly | Not checked as a story | The JSON file writer is built and tested (for LS-S8); this story's own acceptance criteria have not been run. | tests/test_result_file_unit.py (16 passed)
OUT-S3 | OUT Save & deliver (database + JSON) | One upload gives one result, even if repeated or interrupted | Should | 2 | 2 | 3 | Partial | No | - | Not taken up yet. | -
ENT-S1 | ENT Enterprise readiness | Commercial licence audit of every software, model, data set and code list | Must | 1 | 3 | 5 | Not built | No | - | Not taken up yet. | -
ENT-S2 | ENT Enterprise readiness | Sign-in, roles and an audit trail | Must | 1 | 6 | 8 | Not built | No | - | Not taken up yet. | -
ENT-S3 | ENT Enterprise readiness | Prove the accuracy: an answer-key set and an automatic quality gate | Must | 1 | 7 | 8 | Not built | No | - | Not taken up yet. | -
ENT-S4 | ENT Enterprise readiness | Run it reliably: health, metrics, alerts, backups and a restart runbook | Should | 2 | 4 | 5 | Partial | No | - | Not taken up yet. | -

## Summary
Summary - counted from the 'Backlog status' sheet
Epic | Stories | Yes | Yes - open items | Partly | No | Built (Yes + Yes - open items) | Share built
UP Scan & upload screen
LS File listener (watched folder)
IM Image preparation (OpenCV)
RD Reading engines working together
SW Change any model or component
EX The four things we extract
OUT Save & deliver (database + JSON)
ENT Enterprise readiness
TOTAL
'Built' counts a story once its code is written and tested; 'Yes - open items' stories still have a criterion that is partial or waits on outside input - see the 'Backlog status' sheet.
Nothing after LS-S4 is committed or pushed to GitHub yet (as of 2026-10-10).